VIVO FASHION GROUP

Data Prep Brief — Project Reconnect Micro-Test Programme

Building the raw cohort and test-allocation data for the August–September test programme

| To | William |
| --- | --- |
| From | Achieng — Head of Retail & Customer Experience |
| Re | Cohort creation and test-allocation data for the churn micro-test programme |
| Needed by | Before 24 Aug launch — ideally w/c 17 Aug to allow QA time |

# What I need

Raw, allocated cohort data for the full micro-test programme: 15 tests, run identically across two churn cohorts, with every customer assigned to exactly one test arm. This replaces the earlier 4-test Churn Test Programme data pull — please build fresh from the brief below rather than extending that one.

# Source data

Start from the same cleaned Kenya reactivation list we've been using (contactable, Kenya-only, excluding the 54 wholesale/staff accounts and ~6,400 malformed/non-Kenya contacts). If you've pulled a fresher export since 12 Aug, use that instead — just note the pull date and re-confirm the population counts below still roughly hold.

# Cohort definitions

Two cohorts, based on Vivo's current churn definition — not the 90–180 day “Warm” framing we used earlier:

| Cohort | Definition | Approx. population | Approx. LTV |
| --- | --- | --- | --- |
| At-Risk | 6–12 months since last purchase | 30,996 | KES 1.51B |
| True Churn | 12+ months since last purchase | 98,127 | KES 1.81B |
| Excluded | Under 6 months — out of scope for this programme | 11,468 | KES 0.66B |

Please recompute these three counts from your pull and flag if they differ meaningfully from the figures above — that's a sign the underlying data has shifted since our last export.

# Test list and sample sizes

Every test below runs identically in both cohorts — same arms, same sample size per arm — so each customer should be tagged with both their Cohort and their Test/Arm assignment. No customer should appear in more than one test.

| Test | Arms | Sample/arm |
| --- | --- | --- |
| M1 · Relevant/newness vs. generic | 2 | 800 |
| M2 · Newness-led vs. relationship-led | 2 | 800 |
| M3 · Store-specific vs. Vivo-wide | 2 | 800 |
| I1 · No incentive vs. 5% | 2 | 800 |
| I2 · 5% vs. 10% | 2 | 800 |
| I3 · Recognition vs. small gift | 2 | 800 |
| C1 · Emotional vs. commercial tone | 2 | 800 |
| C2 · Short vs. longer copy | 2 | 800 |
| C3 · Product image vs. text-only | 2 | 800 |
| J1 · One touch vs. two vs. no-contact | 3 | 800 |
| J2 · 3–4 day vs. 7–10 day reminder | 2 | 800 |
| CH1 · WhatsApp vs. SMS | 2 | 800 |
| CH2 · WhatsApp vs. Email newsletter | 2 | 800 — see Q1 |
| CH3 · SMS vs. Email newsletter | 2 | 800 — see Q1 |
| CH4 · Best digital channel vs. phone call | 2 | ~150 — high-value only, see Q7 |

That's ~23,500 people per cohort for this round (~47,000 total) — comfortably inside True Churn's pool, but roughly 76% of At-Risk's. If At-Risk can't support the full list, tell me rather than silently shrinking sample sizes — we'd rather cut a test than underpower all of them.

# Sampling method

- Stratify each test's arms by value band (High ≥KES 100K LTV / Medium KES 20K–99K / Low <KES 20K) so every arm gets a comparable mix — pure random allocation risks one arm landing disproportionately high- or low-value by chance.

- Assign customers to tests without replacement — once someone is allocated to a test/arm, remove them from the pool before allocating the next test.

- If you have a documented method you'd rather use for the stratified draw, go with it — just note what you did so we can reproduce it later.

# Open questions — need your input before/while building this

Q1.  Email addresses: the reactivation list has no email field, which blocks CH2 and CH3 as designed. Is there a separate Shopify/CRM export with customer emails I should ask for, or should I drop those two tests from this round?

Q2.  Customer names: the file has phone numbers but no name field, and every message template uses [First Name]. Is there a name-lookup source you can join in, or does personalization get handled downstream by whatever platform sends the messages?

Q3.  Suppression list: beyond the exclusions already applied, is there a list of customers currently in another live campaign (VIVO15 follow-up, store promos, etc.) I should exclude before allocation? The “one customer, one experimental cell” rule depends on this.

Q4.  Output format: would an Excel workbook work — one tab per test plus a master summary tab, each with Contact, Cohort, Arm, Days Since, LTV, and Value Band for QA? Or would separate CSVs per test, or one flat file with Test/Arm as columns, be easier on your end?

Q5.  Contact formatting: the file mixes +254 international format and local 0-prefixed numbers. Should everything be normalized to full international format before it goes to Emmerce, or does the platform handle that on ingest?

Q6.  Recency boundary precision: I've used ≥182 days as the At-Risk start and ≥365 days as True Churn — confirm these are the right day-count boundaries for “6 months” and “12 months”, or if Vivo uses a different convention (30-day months vs. calendar months, etc.).

Q7.  CH4 high-value threshold: confirming this means LTV ≥ KES 100,000, same as the “High” value band used everywhere else — and separately, what's a realistic per-agent daily call capacity, so ~150/arm is actually achievable in the test window rather than a number I picked without checking against real capacity?

IF SOMETHING DOESN'T RECONCILE If your pull gives meaningfully different population counts than the ~30,996 / ~98,127 figures above, or if the stratified draw can't hit target sample sizes for any test, please flag it rather than adjusting silently — we'll want to know before this goes live, not after.